SOLFACIL  |  EOS Partner Pilot Program

Full-Stack Hardware + Software

Gateway + HEMS Optimization + VPP/Trading + Customer App

GOAL: Validate the functionality and level of “deployment readiness” for each part of the end-to-end energy operating system: physical gateway/edge control that survives Brazilian infrastructure challenges, plus software stack (HEMS optimization, VPP aggregation, trading functionality, and customer app). 

POST-PILOT NEXT STEPS: Based on this validation, we will (a) determine which part(s) we could potentially partner on together vs. which part(s) we should get from other vendors, and (b) commence commercial discussions. We would be thrilled if one provider could do everything exceptionally well. However, we think this is unlikely, so we expect to “mix and match” capabilities across vendors.

| Timeline | Ship hardware to Brazil by Jan 26 Receive hardware in Brazil by Feb 16 Install hardware & set up software by March 2 Initial “High Quality” data by March 31 Full results complete by May 2 Note: As we begin to receive technical results in March, we can start commercial discussions if things seem promising for both sides |
| --- | --- |

What Solfacil Brings

- 2-3 pilot homes with diverse conditions (127V/220V, fiber/4G, clean/messy wiring)

- Real Brazilian infrastructure challenges for stress testing (outages, voltage drops)

- Brazilian tariff data (Tarifa Branca, which is our “Time of Use” tariff) + future dynamic pricing roadmap

- Simulated VPP/DR events for dispatch accuracy testing - we will do a proxy test by controlling loads & logging events on pilot sites

- Hardware shipping/customs support + integrator partner for commissioning

- If the partnership is successful, path to 300K+ homes over time and participation in Brazil's emerging VPP/trading markets

What We Need From You

- Physical gateway/controller hardware shipped to Brazil (60Hz, 127V/220V compatible), if relevant

- Edge intelligence that operates during internet outages (72hr+)

- HEMS optimization engine (self-consumption, Time of Use arbitrage, peak shaving)

- Ability to load tariffs & economic optimization rules to feed the simulations (whether you do it or we do it)

- VPP/fleet aggregation dashboard + DR dispatch capability

- The ability to see how customer export and load behavior (charge/discharge/shift) changes in response to the rules that are set

- White-label customer app & monitoring portal

- API access for Solfacil integration

- List of devices you are API integrated with so we can pick compatible hardware for the pilot - smart meter, battery/inverter, ACs, EV Chargers

Success Criteria

OBJECTIVE 1: Works in Brazil (Week 1) — Hardware + Basic Software

Hardware & Connectivity:

- Gateway installs & commissioned in <2 hours by integrator

- System survives 72 hour WiFi dropout (offline schedule continues; data is properly stored and sent back to cloud upon resumption of connectivity)

- RS485/Modbus wiring option works (meter at gate → inverter in garage, ACs inside the house, EV charger in the driveway)

- 60Hz grid + both 127V and 220V configurations validated

Software & App:

- Customer app white-labels cleanly (eg: all data & info loads cleanly, no “unsolvable” recurring errors, etc.)

- Admin monitoring interface white labels cleanly (eg: all data & info loads cleanly, no “unsolvable” recurring errors, etc.)

- Ideally app & monitoring portal load in <5 seconds upon initial opening

- Admin can set rules for HEMS optimization effectively, including for VPP and Energy Trading, eg: rules are set and they are proven to work as evidenced by system-level & device-level performance

- Tarifa Branca can be loaded into the system in <2 days

- The ability to see customer export and load behavior overall for the home & by device that is being controlled

- Connects to a minimum of 1 Brazilian inverter brand that we use (Growatt, Sofar, Goodwe, Huawei, Solis, Deye) + 1 AC + 1 EV Charger + 1 Smart Meter

- First telemetry data for full set of devices within 24 hours of install; >90% uptime over 4 weeks

OBJECTIVE 2: Creates Monetizable Value (Weeks 2-8) — Optimization + VPP

Optimization Performance:

- >70% of theoretical maximum savings achieved (shadow benchmark vs. 'dumb' baseline)

- Tarifa Branca (“Time of Use”) optimization working (correct charge/discharge timing for peak/off-peak)

- For Solar+Battery Systems, >98% self-consumption achieved across pilot homes, eg: do not violate self-consumption by accident

- PV forecast MAPE <25%; load forecast adapts within 2 weeks

VPP & Grid Services:

- VPP dispatch accuracy >85% (request 5kW → deliver 4.25kW+)

- 90%+ performance of 15+ minute latency functions (we will do latency tests of 1s / 5s / 15s / 30s / 1 min / 15 min / 1h / day ahead)

- Demand limiting response [latency TBD; we may have an opportunity to shape these specifications]

- Fleet dashboard operational with aggregate view across pilot homes

Deployment & Economics:

- Gateway BOM cost <$35 FOB at scale of 50K+/yr; 24hr optimization schedule stored locally

- Integrator can commission solo after <90 minute training

- API documented and accessible for Solfacil master app integration

Key Metrics We'll Track

Hardware: Commissioning time • Offline resilience (hrs) • Demand response latency (sec) • Gateway FOB cost ($)

Software: Optimization alpha (% of theoretical) • Self-consumption (%) • VPP dispatch accuracy • Forecast MAPE • Demand response latency (sec)

Experience: Integrator training time • Manual interventions (#) • App uptime

Questions? Contact Brian Korgaonkar | brian@solfacil.com.br